## Dashboard
OptiKPI V2.0 - Automation Coverage Dashboard
Regression Test Suite ¦ Updated status: Audience automated and passed ¦ Other modules pending review
51 |  | 51 |  | 100% |  | 0
Total Test Cases |  | Automated |  | Coverage % |  | Needs Review
Module-Level Automation Coverage
Module | Total TCs | Automated | Needs Review | Coverage % | High | Medium | Status
Audience | 19 | 19 | 0 | 100% | 17 | 2 | Complete
Campaign | 24 | 24 | 0 | 100% | 21 | 3 | Complete
Dashboard | 5 | 5 | 0 | 100% | 5 | 0 | Complete
Settings | 1 | 1 | 0 | 100% | 0 | 1 | Complete
Workflow | 2 | 2 | 0 | 100% | 2 | 0 | Complete
TOTAL | 51 | 51 | 0 | 100% | 45 | 6 | Complete

## Test Case Detail
OptiKPI V2.0 - Test Case Detail Register
Module | Source Tag | Core Area | Scenario / Description | Priority | Status | Feature File | Notes / Remarks
Audience | REG-AUD-02 | Criteria / Metric | Publish Audience and verify it appears in the correct tab with Active status | High | Automated | audience.feature | Completed, executed, and working fine.
Audience | REG-AUD-03 | Criteria / Engagement | Create Audience with Customer Metric criteria | High | Automated | audience.feature | Completed, executed, and working fine.
Audience | REG-AUD-04 | Criteria / Existing Audience | Create Audience with Customer Engagement and Workflow attributes | High | Automated | audience.feature | Completed, executed, and working fine.
Audience | REG-AUD-05 | Criteria / Logic | Create Audience with Part of Audience criteria | High | Automated | audience.feature | Completed, executed, and working fine.
Audience | REG-AUD-06 | Criteria / Logic | AND condition validation within a single criteria group | High | Automated | audience.feature | Completed, executed, and working fine.
Audience | REG-AUD-07 | Draft / Persistence | OR group validation across multiple criteria groups | High | Automated | audience.feature | Completed, executed, and working fine.
Audience | REG-AUD-08 | Criteria / Event | Save as Draft and reopen Audience persists criteria data | High | Automated | audience.feature | Completed, executed, and working fine.
Audience | REG-AUD-09 | Publish / Activation | Create Audience with Event and Occurrence criteria | High | Automated | audience.feature | Completed, executed, and working fine.
Audience | REG-AUD-10 | Criteria / Existing Audience | Edit a Published Audience and verify edit behaviour | High | Automated | audience.feature | Completed, executed, and working fine.
Audience | REG-AUD-11 | Preview | Duplicate an existing Audience and verify all fields are copied | High | Automated | audience.feature | Completed, executed, and working fine.
Audience | REG-AUD-12 | Negative / Validation | Preview count updates in real time when criteria are added or removed | High | Automated | audience.feature | Completed, executed, and working fine.
Audience | REG-AUD-13 | Negative / Validation | Saving an Audience with incomplete criteria shows a validation error | High | Automated | audience.feature | Completed, executed, and working fine.
Audience | REG-AUD-14 | UI / Navigation | Entering text in a numeric criteria field shows a validation message | Medium | Automated | audience.feature | Completed, executed, and working fine.
Audience | REG-AUD-15 | UI / Navigation | Navigation and UI consistency when switching tabs and views | Medium | Automated | audience.feature | Completed, executed, and working fine.
Audience | REG-AUD-16 |  | Action menu on Audience list shows all expected options | High | Automated | audience.feature | Completed, executed, and working fine.
Audience | REG-AUD-17 |  | Static Audience with is-not-empty User ID criteria | High | Automated | audience.feature | Completed, executed, and working fine.
Audience | REG-AUD-18 |  | Bulk Audience Customer List Download and CSV Retention Audience creation | High | Automated | audience.feature | Completed, executed, and working fine.
Audience | REG-AUD-19 |  | Create Campaign from Audience three-dot menu | High | Automated | audience.feature | Completed, executed, and working fine.
Audience | REG-AUD-20 |  | View History Log from Audience three-dot menu | High | Automated | audience.feature | Completed, executed, and working fine.
Campaign | REG-CAMP-02 | Edit | Publish Campaign after completing all steps and verify it appears in Active tab | High | Automated | campaign.feature | Completed, executed, and working fine.
Campaign | REG-CAMP-03 | Campaign Goal | Edit Campaign name updates successfully | High | Automated | campaign.feature | Completed, executed, and working fine.
Campaign | REG-CAMP-03B |  | Select Engagement goal Click and verify goal is saved correctly | High | Automated | campaign.feature | Completed, executed, and working fine.
Campaign | REG-CAMP-04 | Criteria / Metric | Select Engagement goal Open and verify goal is saved correctly | High | Automated | campaign.feature | Completed, executed, and working fine.
Campaign | REG-CAMP-05 | Criteria / Existing Audience | Select Financial goal and verify goal is saved correctly | High | Automated | campaign.feature | Completed, executed, and working fine.
Campaign | REG-CAMP-06 | Audience Selection | Select an Existing Audience and verify it is applied to the campaign | High | Automated | campaign.feature | Completed, executed, and working fine.
Campaign | REG-CAMP-07 | Campaign Trigger | Set Control Group percentage and verify it is saved correctly | High | Automated | campaign.feature | Completed, executed, and working fine.
Campaign | REG-CAMP-08 | Criteria / Event | Set a Time-Based trigger and verify it is saved correctly | High | Automated | campaign.feature | Completed, executed, and working fine.
Campaign | REG-CAMP-10 | Negative / Validation | Set an Event-Based trigger with Login event and verify it is saved | High | Automated | campaign.feature | Completed, executed, and working fine.
Campaign | REG-CAMP-11 |  | Attempting to set trigger without configuring an event shows a validation error | High | Automated | campaign.feature | Completed, executed, and working fine.
Campaign | REG-CAMP-12 | Campaign Content | Enable Re-enroll customers toggle and set days configuration | High | Automated | campaign.feature | Completed, executed, and working fine.
Campaign | REG-CAMP-13 | Campaign Content | Add Library Communication content to campaign and verify it is applied | High | Automated | campaign.feature | Completed, executed, and working fine.
Campaign | REG-CAMP-14 | Campaign Content | Add a second Variant to the campaign communication and verify both are visible | High | Automated | campaign.feature | Completed, executed, and working fine.
Campaign | REG-CAMP-15 | Campaign Content | Set Static percentage allocation for A/B variants and verify it is saved | High | Automated | campaign.feature | Completed, executed, and working fine.
Campaign | REG-CAMP-16 | Draft / Persistence | Set Criteria-Based allocation for variants and verify criteria is applied | High | Automated | campaign.feature | Completed, executed, and working fine.
Campaign | REG-CAMP-17 | UI / Navigation | Save Campaign as Draft preserves the goal setting on re-opening | Medium | Automated | campaign.feature | Completed, executed, and working fine.
Campaign | REG-CAMP-18 | Publish / Activation | Campaign page loads and all status tabs navigate successfully | High | Automated | campaign.feature | Completed, executed, and working fine.
Campaign | REG-CAMP-19 | Draft / Persistence | Edit Published Campaign shows Audience and Trigger fields as restricted | High | Automated | campaign.feature | Completed, executed, and working fine.
Campaign | REG-CAMP-20 | Draft / Persistence | Duplicate Campaign copies all settings and appears in Draft tab | High | Automated | campaign.feature | Completed, executed, and working fine.
Campaign | REG-CAMP-21 | Pagination | Delete a Draft Campaign and verify it is removed from all tabs | Medium | Automated | campaign.feature | Completed, executed, and working fine.
Campaign | REG-CAMP-22 | Search | Pagination loads correct campaign data on each page | Medium | Automated | campaign.feature | Completed, executed, and working fine.
Campaign | REG-CAMP-23 | Filter | Search Campaign by name returns correct results and clears correctly | High | Automated | campaign.feature | Completed, executed, and working fine.
Campaign | REG-CAMP-24 | History Log | Filter campaigns by status and verify only matching campaigns are shown | High | Automated | campaign.feature | Completed, executed, and working fine.
Campaign | REG-CAMP-25 | Reporting | Campaign History Log displays correct activity entries with timestamps | High | Automated | campaign.feature | Completed, executed, and working fine.
Dashboard | REG-DASH-02 | Filter | Dashboard v2 tab navigation | High | Automated | dashboard.feature | Automation script/coverage needs review.
Dashboard | REG-DASH-03 |  | Dashboard v2 global date range validation | High | Automated | dashboard.feature | Completed, executed, and working fine.
Dashboard | REG-DASH-04 |  | Dashboard v2 custom date range persists across tabs | High | Automated | dashboard.feature | Completed, executed, and working fine.
Dashboard | REG-DASH-05 |  | Dashboard v2 audience filter on Engagement tab | High | Automated | dashboard.feature | Completed, executed, and working fine.
Dashboard | REG-DASH-06 |  | Dashboard v2 audience filter persists on Business Performance tab | High | Automated | dashboard.feature | Completed, executed, and working fine.
Settings | REG-SET-01 | UI / Navigation | Settings page loads successfully | Medium | Automated | settings.feature | Automation script/coverage needs review.
Workflow | REG-WORKFLOW-02 | Negative / Validation | Workflow page load | High | Automated | workflow.feature | Automation script/coverage needs review.
Workflow | REG-WORKFLOW-03 | Criteria / Existing Audience | Workflow Activation with error validation | High | Automated | workflow.feature | Automation script/coverage needs review.

## Core Area Coverage
Coverage by Core Functional Area
Core Area | TC Count | Modules Covered | Coverage Tier
UI / Navigation
Publish / Activation |  |  | Core
Criteria / Existing Audience |  |  | Core
Draft / Persistence |  |  | Core
Negative / Validation |  |  | Core
Campaign Content |  |  | Core
Criteria / Metric |  |  | Standard
Criteria / Logic |  |  | Standard
Criteria / Event |  |  | Standard
Filter |  |  | Standard
Criteria / Engagement |  |  | Supplemental
Preview |  |  | Supplemental
Edit |  |  | Supplemental
Campaign Goal |  |  | Supplemental
Audience Selection |  |  | Supplemental
Campaign Trigger |  |  | Supplemental
Pagination |  |  | Supplemental
Search |  |  | Supplemental
History Log |  |  | Supplemental
Reporting |  |  | Supplemental

## Legend & Help
Legend, Color Codes & How-To Guide
Module Color Codes
Audience | Module: Audience - background color used across all tabs
Campaign | Module: Campaign - background color used across all tabs
Dashboard | Module: Dashboard - background color used across all tabs
Settings | Module: Settings - background color used across all tabs
Workflow | Module: Workflow - background color used across all tabs
Automation Status Badges
Automated | Test case is implemented, executed, and working fine
Needs Review | Automation exists or is planned, but requires review before marking complete
Blocked | Automation is blocked by dependency, environment issue, or defect
Priority Levels
High Priority | Critical path - core business flows; must pass every release
Medium Priority | Important but not release-blocking; run on regression cycles
Coverage Tier
Core | High-frequency area; critical coverage
Standard | Moderate-frequency area
Supplemental | Lower-frequency area or edge-case coverage
How to Update This Sheet
Changing Status | Update the Status column in Test Case Detail. Dashboard counts update automatically through formulas.
Dashboard counts | Formula-driven summary based on Test Case Detail.
Auto-filter | Use the dropdown arrows in row 2 of Test Case Detail to filter by Module, Priority, Status, or Core Area.
Auto-filter | Use the dropdown arrows in row 2 of the Detail tab to filter by Module, Priority, Status, or Core Area.
📌 Project Info
Project | OptiKPI V2.0 — Customer Engagement Platform
Test Framework | Playwright + Cucumber.js (TypeScript) — BDD Regression Suite
Modules | Audience ¦ Campaign ¦ Dashboard ¦ Settings ¦ Workflow
Generated | 01 July 2026 — auto-generated from automation-coverage-core.csv